# Timeline — The National Lottery Community Fund — National Lottery Awards for All England

No closing date: a rolling programme. About 18 hours of work in total.

| Date | Days before deadline | Task | Owner |
| --- | --- | --- | --- |
|  | 21 | Coordinator drafts project narrative and outcomes section | Coordinator |
|  | 16 | Finance lead compiles budget, match funding evidence, reserves approval | Finance Lead |
|  | 14 | Designated safeguarding lead reviews compliance and governance attachments | Designated Safeguarding Lead |
|  | 10 | Trustee chair reviews full draft application and sign-off | Trustee |
|  | 7 | Coordinator incorporates feedback and finalises supporting evidence pack | Coordinator |
|  | 3 | Finance lead audits all figures against Xero and submits application | Finance Lead |

When a step is done, add its task to 05-timeline/done.txt, one per line. The next run checks what is left against the time left.